## Overview
Section | Field | Details | Phases | Estimated Time | Milestones | Status
Project identity | Project name | AI-Assisted Release Documentation Triage Workflow | Project setup and product definition | 3–4 hours | Milestone 1: DeskPilot 2.4 source pack
Project identity | AI transparency note | This is a deliberately AI-assisted, fictional portfolio project. I used AI to create and test a realistic documentation workflow, then evaluated, revised, and validated the outputs as a technical writer would. I also used AI to support project planning, including the work breakdown structure, tracker design, prompt log, and review process.
Project identity | Fictional product | DeskPilot | Source input creation | 6 hours
Project identity | Release | DeskPilot 2.4 | AI workflow prompts and outputs | 6–7 hours
Project identity | Project format | GitHub repository with optional GitHub Pages view | Writer validation and final docs | 4–5 hours
Project management | Project goal | Build a portfolio-ready AI-assisted workflow that shows how messy release inputs can be turned into validated customer-facing release documentation. | Case study and GitHub publishing | 6–8 hours
Project management | Project scope | Create fictional release inputs, use AI to generate a draft release contents table, validate the output as a technical writer, draft release notes and a KB update plan, validate the draft outputs, and publish the workflow as a GitHub Pages case study. | Final review and positioning | 2–3 hours
Project management | Success criteria | The project is complete when I can publish a GitHub repository case study showing how DeskPilot 2.4 source inputs were processed into generated release contents, final release notes, a validated KB update plan, and a writer validation checklist. |  | 20-28 hours
Project management | Estimated effort | 15–22 hours from revised workflow rebuild Note: Time estimates represent approximate project effort, including prompting, review, editing, formatting, and alignment across files. They are not stopwatch measurements.
Project management | First milestone | DeskPilot 2.4 source pack
Portfolio purpose | Portfolio goal | Demonstrate how I can use AI to support release discovery, documentation triage, drafting, KB impact analysis, and writer-led validation. | DeskPilot Users
Portfolio purpose | Primary audience | Hiring managers, recruiters, and documentation/content teams interested in AI-assisted documentation workflows. | Support agent | Responds to tickets, uses saved replies, checks customer history
Portfolio purpose | Capability demonstrated | Maintaining high-velocity documentation updates while preserving human review, accuracy, clarity, source alignment, and publishing control. | Support team lead | Monitors queues, assigns work, reviews performance
Product context | Product type | SaaS support ticketing and customer service platform | Admin | Configures automations, permissions, tags, integrations
Product context | Product description | DeskPilot is a fictional SaaS customer support platform for small and mid-sized businesses. It helps support teams manage customer tickets, automate routine workflows, track service-level targets, and maintain a customer-facing knowledge base. | Customer | Submits tickets and searches the help centre
Product context | Target users | Support agents, support team leads, workspace admins, and customers.
Product context | Release theme | Faster support workflows, clearer automation controls, and improved ticket visibility.
Inputs and outputs | Main inputs | Jira tickets; feature notes; Git commits; support feedback.
Inputs and outputs | Main workflow steps | Generate draft release contents; validate release contents; draft release notes; create KB update plan; validate AI-generated outputs; prepare final documentation package.
Inputs and outputs | Main outputs | Generated release contents table; release contents validation notes; draft release notes; draft KB update plan; validation findings; final release notes; validated KB update plan; writer validation checklist; case study.
Scope boundaries | In scope | Fictional Jira ticket data; feature notes; Git commit log; support feedback; AI prompts; generated release contents; AI-generated draft outputs; writer validation; final release notes; KB update plan; GitHub Pages case study.
Scope boundaries | Out of scope | Building a full production app; integrating with real Jira or GitHub APIs; creating a real SaaS product; automating publishing to a live documentation platform.
Project Kick-off | 2026-05-31 | Original start date
Project Revision | 2026-06-04 | Revised start date (after I decided to revise the AI workflow)
Project Complete | 2026-06-05

## WBS Tracker
WBS ID | Phase | Task Name | Description | Estimated Effort | Status | Notes | Next Action
1R | Scope revision | Revise project scope | Update the project scope from an AI-assisted release notes workflow to an AI-assisted release documentation triage workflow. | 30 mins | Complete | Reflects the new workflow where AI generates the release contents list from messy inputs. | Update Overview tab.
1.1R | Scope revision | Revise project goal and success criteria | Update goal, scope, success criteria, in-scope, and out-of-scope items for the revised workflow. | 30 mins | Complete | Project now demonstrates release discovery, triage, release notes, KB planning, and validation. | Update workbook Overview.
1.2R | Scope revision | Create revised project folder structure | Create a new project folder and archive the old baseline workflow separately. | 45 mins | Complete | Revised folder structure created for the simplified release documentation triage workflow. | Save generated release contents in 02-ai-processing.
2R | Product and release design | Define fictional product context | Define DeskPilot as a fictional SaaS customer support platform, including users, customer types, and release context. | 1 hour | Complete | DeskPilot product context defined for use across source inputs, prompts, and case study. | Create fictional release source inputs.
3R | Source input design | Create fictional Jira tickets | Create realistic Jira-style tickets for DeskPilot 2.4, including features, improvements, fixes, admin updates, and known issues. | 1.5 hours | Complete | Jira tickets created as messy source material for the AI triage workflow. AI assisted with this task. | Create feature notes.
3.1R | Source input design | Create fictional feature notes | Create rough product-manager style notes for major release items, customer value, and writer flags. | 1 hour | Complete | Feature notes created to provide product context and validation caveats. | Create Git commit log.
3.2R | Source input design | Create fictional Git commit log | Create realistic commit-style entries with a mix of customer-facing changes and internal technical noise. | 1 hour | Complete | Git commits created to test whether AI can separate customer-facing changes from implementation detail. | Create support feedback.
3.3R | Source input design | Create fictional support feedback | Create support/customer feedback records linked to release issues and documentation signals. | 1 hour | Complete | Support feedback created to show customer impact and KB update signals. | Run P-000 to generate release contents.
5R | Workflow design | Design revised AI-assisted triage workflow | Define simplified workflow: messy inputs, generated release contents, writer validation, draft release notes, KB plan, validation, final outputs. | 1 hour | Draft complete | Workflow has been discussed and simplified. | Record revised workflow table.
5.1R | Workflow design | Update Prompt Log for revised workflow | Keep P-000, P-003, P-004, and P-005. Archive P-001 and P-002 as baseline prompts. | 30 mins | Complete | Prompt Log needs to match simplified workflow. | Update Prompt Log.
5.2R | Workflow design | Update workflow diagrams | Update Mermaid flowchart and sequence diagram to include P-000, P-003, P-004, and P-005. | 30 mins | Draft complete | Updated diagrams drafted in conversation. | Add diagrams to case study.
6R | AI processing outputs | Run P-000 to generate release contents | Use messy inputs only: Jira tickets, feature notes, Git commits, support feedback. Generate release contents from source inputs. | 45 mins | Complete | Completed in Claude. Output generated as Word document/table. | Save output as generated-release-contents.md or csv.
6.1R | AI processing outputs | Save generated release contents | Save Claude-generated release contents in the new repo under 02-ai-processing. | 30 mins | Complete | Generated release contents saved as project artefact. Use generated-release-contents.md | Create release contents validation notes.
7R | Writer validation | Validate generated release contents | Review generated release contents for source alignment, exclusions, caveats, unsupported claims, and product confirmation needs. | 1 hour | Complete | Release contents validation notes created (release-contents-validation-notes.md). Generated release contents accepted as the working source for draft release notes and KB planning, with caveats recorded. | Run P-004 to draft release notes from generated release contents.
6.2R | AI processing outputs | Run P-004 to draft release notes from generated release contents | Test whether draft release notes can be generated using only the generated/validated release contents table. | 45 mins | Complete | Draft release notes generated from generated release contents only, proving the simplified workflow works without extracted-changes or grouped-release-items files. (draft-release-notes.md) | Run P-003 to create KB update plan.
6.3R | AI processing outputs | Run P-003 to create KB update plan | Create a draft KB update plan from the generated/validated release contents table. | 45 mins | Complete | Draft KB update plan generated from generated release contents only. | Run P-005 to validate generated release contents, draft release notes, and KB update plan against original source inputs.
6.4R | AI processing outputs | Run P-005 to validate documentation outputs | Validate generated release contents, draft release notes, and KB update plan against original source inputs. | 1 hour | Complete | Key responsible AI validation step. Validation findings generated for release contents, draft release notes, and KB update plan against original source inputs. | Edit draft release notes into final version.
7.2R | Writer validation | Edit draft release notes into final version | Apply validation findings and writer judgement to create final release notes. | 1.5–2 hours | Complete | Editing draft release notes using validation findings and writer judgement. | Create final-release-notes.md.
7.3R | Writer validation | Create validated KB update plan | Review draft KB plan and create final writer-approved KB update plan. | 1 hour | Complete | Validated KB update plan created after reviewing draft KB plan, generated release contents, and validation findings. | Create validated-kb-update-plan.md.
7.4R | Writer validation | Update writer validation checklist | Adjust checklist to include release contents validation as well as draft release notes and KB plan validation. | 30 mins | Complete | Writer validation checklist updated to reflect the revised workflow, including generated release contents, draft release notes, KB update plan, and final approval. | Create revised documentation package.
8R | Publishing package | Create revised documentation package | Organise source inputs, AI outputs, validation notes, final outputs, prompts, and case study in the new folder structure. | 1 hour | Complete | Revised project package organised around the simplified workflow: messy source inputs, generated release contents, writer validation, draft outputs, validation findings, and final documentation. | Update README for revised workflow.
8.1R | Publishing package | Update README for revised workflow | Rewrite README to describe the revised release documentation triage workflow. | 1 hour | Complete | README updated to describe the revised release documentation triage workflow, including generated release contents, writer validation, final outputs, and repo structure. | Write new case study.
8.2R | Publishing package | Export project tracker tabs for GitHub viewing | Export key workbook tabs as Markdown or CSV so reviewers can inspect the project overview, WBS, decision log, prompt log, prompt run log, and validation log without opening Excel. | 45 mins | Complete | The Excel workbook remains the source tracker, but exported files make the project management evidence easier to view in GitHub. | Update README links to project management artefacts.
9R | Case study | Write new case study | Write fresh case study based on revised workflow, without relying on baseline workflow. | 2–3 hours | Complete | New case study draft created for the revised workflow. Review for clarity, links, and consistency. | Add reflection on worfklow simplification.
9.1R | Case study | Add updated workflow section | Add revised workflow diagram, sequence diagram, and workflow stages table. | 45 mins | Draft complete | Diagrams drafted. | Add to case study.
9.2R | Case study | Add estimated time impact section | Add revised time impact table for simplified workflow. | 30 mins | Draft complete | Updated section drafted. | Add to case study.
9.3R | Case study | Add reflection on workflow simplification | Explain that generated release contents replaced separate extract/group steps. | 45 mins | Complete | Reflection added explaining that generated release contents became the central source for drafting release notes and KB updates. | Prepare local repo for upload.
10R | GitHub publication | Prepare local repo for upload | Check revised folder structure, Markdown rendering, file names, diagrams, and links. | 1 hour | Complete | Checking revised folder structure, Markdown rendering, file names, Mermaid diagrams, links, and consistency before creating the GitHub repository. | Create GitHub repository.
10.2R | GitHub publication | Create GitHub repository | Create/push revised project repo. | 45 mins | Complete | Creating GitHub repository and uploading revised project files. | Enable GitHub Pages or review repo on GitHub.
10.3R | GitHub publication | Enable GitHub Pages | Configure GitHub Pages if needed. | 45 mins | Complete | Pages was enabled, but GitHub repository view was chosen as the main portfolio link because it renders Mermaid diagrams correctly and better exposes the project structure. | Review GitHub repo view.
10.4R | GitHub publication | Review GitHub repo view | Check links, formatting, readability, and diagrams after publishing. | 1 hour | Complete | Reviewing the GitHub repository as the main project link, including README, case study, diagrams, links, file structure, and final outputs. Findings added to Validation Log tab. | Fix issues found if applicable
10.5R | GitHub publication | Fix issues from GitHub repo review | Resolve formatting, link, diagram, wording, or file-structure issues found during the GitHub repo review. | 1 hour | Complete | Use the Validation Log to track issues such as truncated Mermaid labels, broken links, or unclear file references, and push changes to GitHub. | Map project to job capabilities.
11R | Portfolio positioning | Map project to job capabilities | Map revised project to high-velocity updates, AI workflow design, release triage, KB maintenance, and validation. | 1 hour | Not started | Useful for applications/interviews. | Create capability map.
11.1R | Portfolio positioning | Write short portfolio summary | Write short description for portfolio, LinkedIn, or job applications. | 45 mins | Not started | Do after case study is stable. | Draft summary.
12R | Final review | Conduct final quality review | Check that evidence supports claims, workflow is coherent, files are consistent, and case study is clear. | 1.5 hours | Not started | Final review after publication or local completion. | Complete project.

## Decision Log
Decision ID | Date | Decision | Context | Rationale | Impact / Action
DEC-001 | 2026-06-04 | Use GitHub repository as the main project link | The project was tested in both GitHub Pages and standard GitHub repository view. GitHub Pages rendered the Markdown content but did not render Mermaid diagrams as diagrams and did not add useful navigation for this simple project. GitHub repository view renders Mermaid diagrams correctly, shows the file/folder structure, supports page outlines, and makes the source inputs, prompts, AI outputs, validation notes, and final outputs easier to inspect. | The GitHub repository will be used as the primary project link from the portfolio site. GitHub Pages can remain enabled as a secondary option, but the portfolio call-to-action should point to the repository unless a more polished Pages version is created later. | Add GitHub repo link to portfolio project page. Treat Pages as optional/future enhancement.
DEC-002 | 2026-06-05 | Include AI involvement transparency note | The project is explicitly about an AI-assisted documentation workflow, and AI was used to help generate source materials, prompts, draft outputs, and some case study wording. | Being transparent avoids implying that the project represents a real product release, a measured workplace productivity result, or fully manual authorship. It strengthens the credibility of the portfolio piece by making the role of AI and the role of the writer clear. | Add a transparency note to the case study explaining that DeskPilot and the release inputs are fictional, AI was used to assist the project, and the writer role was to define, guide, review, validate, and shape the final documentation package.
DEC-003 | 2026-06-05 | Describe time estimates as indicative effort only | The case study includes estimated time impact for using an AI-assisted workflow compared with a manual workflow. | The estimates were not produced by a timed productivity study. The wording needs to avoid overstating productivity claims. The estimates should be framed as indicative comparisons based on likely effort, including prompting, review, editing, formatting, validation, and source alignment. | Update the case study time impact section to state that estimates are indicative only and not measured results. Rename workbook time estimate fields to “Estimated effort” if helpful.
DEC-004 | 2026-06-05 | Defer visual mock-ups and supporting images | The case study could be made more engaging with visuals such as DeskPilot UI mock-ups, workflow illustrations, or screenshots of example artefacts. | Images would improve presentation, but they are not required for the core evidence. The current priority is to complete and publish the workflow, prompts, outputs, and validation artefacts. Adding visuals can be handled as a future enhancement. | Do not add images to the first published version. Add a future improvement to explore DeskPilot UI mock-ups or visual summaries later.
DEC-005 | 2026-06-05 | Include source quality reflection in case study | The prototype source inputs (Jira tickets, feature notes etc) included writer-facing notes and documentation signals, but real workplace inputs are often less complete, less consistent, or missing documentation context. | This reflection makes the case study more realistic and avoids implying that real Jira tickets, commits, or feature notes usually provide clean writer-ready information. It also shows that the project models a healthier documentation handoff process. | Added a Source quality subsection to the What I learned section explaining that real source inputs may be incomplete, contradictory, or missing writer-facing notes, and that the prototype intentionally models a more documentation-aware release process.
DEC-006 | 2026-06-05 | Include key project tracker workbook tabs as Markdown or CSV for easy viewing in GitHub | GitHub will usually treat .xlsx as a downloadable binary file, not something it renders nicely in the browser. An Excel workbook will generally be something a reviewer has to download and open in Excel, Google Sheets, or another spreadsheet app. | Reviewers can inspect the project planning without downloading anything, and the Excel workbook is still available as the original working artefact. | Added exports of key tabs to 06-project-management/ project-overview.md wbs-tracker.csv decision-log.csv

## Prompt Log
Prompt ID | Workflow Step | Prompt Name | Purpose | Input Sources | Expected Output | Status | Notes
P-000 | AW-001 | Generate release contents from messy inputs | Generate draft release contents table from messy Jira tickets, feature notes, Git commits, and support feedback for DeskPilot 2.4 release changes. | Jira Tickets; Feature Notes; Git Commits; Support Feedback | Generated Release Contents table | Draft complete | First reusable prompt. Supports release discovery and triage.
P-003 | AW-004 | Create KB update plan | Identify knowledge base articles that may need to be created, updated, deferred, or validated based on the generated release contents. | Generated Release Contents table | KB Update Plan | Draft complete | Used to convert documentation impact notes into a structured KB update plan.
P-004 | AW-005 | Draft release notes | Create a first-pass customer-facing release notes draft from grouped release items and supporting source material. | Generated Release Contents table | AI Draft Release Notes | Draft complete | Output must be treated as a draft requiring writer validation.
P-005 | AW-006 | Validate AI-generated outputs | Check generated release contents, draft release notes, and KB update plan against the original source material for accuracy, clarity, risk, and validation issues. | Generated Release Contents; AI Draft Release Notes; KB Update Plan; Jira Tickets; Feature Notes; Git Commits; Support Feedback | Validation Findings | Draft complete | Supports the writer validation stage and responsible AI use.

## Prompt Run Log
Run ID | Prompt ID | Input Sources | Output Created | Status | Notes
RUN-001 | P-000 | jira-tickets.csv; feature-notes.csv; git-commits.csv; support-feedback.csv | generated-release-contents.csv; generated-release-contents.md | Complete | Prompt generated a draft release contents list from messy source inputs only. The original prepared release contents file was not provided.
RUN-002 | P-004 | generated-release-contents.md | draft-release-notes.md | Complete | Prompt generated draft release notes using only the generated release contents table. No extracted changes or grouped release items were provided.
RUN-003 | P-003 | generated-release-contents.md | draft-kb-update-plan.md | Complete | Prompt generated a draft KB update plan using only the generated release contents table.
RUN-004 | P-005 | generated-release-contents.md; draft-release-notes.md; draft-kb-update-plan.md; release-contents-validation-notes.md; jira-tickets.csv; feature-notes.csv; git-commits.csv; support-feedback.csv | validation-findings.md | Complete | Prompt validated AI-generated documentation outputs against original source inputs and writer validation notes.

## Validation Log
Issue ID | Review Stage | File / Location | Issue Type | Finding | Severity | Recommended Action | Status | Resolution Notes
REV-001 | GitHub repo review | README.md and 05-case-study/case-study.md | Formatting / diagram readability | Some Mermaid diagram task labels were truncated in GitHub rendering, even though they appeared correctly in VS Code preview. | Medium | Shorten Mermaid node labels and move full prompt names/purpose details into the workflow stages table. | Complete | Use short labels such as “P-000: Generate release contents” and avoid long task descriptions inside diagram boxes.
REV-002 | GitHub repo review | Missing project tracker workbook. | Project transparency | The tracker is part of the project evidence. It shows how I scoped, planned, revised, and managed the workflow. If it sits outside the repo, it becomes invisible to anyone reviewing the project. |  | Add this to the repo structure: 06-project-management/ AI_Assisted_Release_Documentation_Workflow_Tracker.xlsx And update your README key files table with: ¦ [Project tracker workbook](06-project-management/AI_Assisted_Release_Documentation_Workflow_Tracker.xlsx) ¦ Optional supporting artefact showing the project overview, WBS tracker, decision log, prompt log, prompt run log, and validation log. ¦ | In progress
REV-003 | GitHub repo review | Missing lesson learned | Missing caveat | The case study needed clearer context that real workplace source inputs may be less structured than the prototype and may not include writer-facing notes. |  | Add a Source quality reflection to the What I learned section. | Complete | Added Source quality subsection and recorded rationale in Decision Log as DEC-005.